## Detailed Budget
A Field Guide to Community Based Adaptation: Field Assignment 6, Chapter 6
Field Assignment 6. Course Project Example: Detailed Budget
By Tim Magee |  | Copyright © 2012, Tim Magee. All rights reserved.
Date: October 28, 2012
Activity | Detail | Unit | Quantity | Unit Price | Donor | CSDi | Totals
Sub-Goal 1 | Health and Hygiene Program |  |  | $US
Output 1.1 | 100 families participated in workshops on consciousness raising for health and hygiene
Activity 1.1.1 | Develop workshop lesson plan
1 | Project director forms 2 person health, hygiene, nutrition and garden program team | Month | 0.5 | 800 |  | 400 | 400
2 | Background research on evidence-based best practices in hand-washing | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.1.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.1.3 | Present workshops
2 | Health and hygiene program team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.1.4 | Provide 3 months follow-up
2 | Health and hygiene program team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 1 | 360 |  | 360 | 360
10 | Office expenses | Unit | 1 | 250 | 250 |  | 250
Output 1.2 | 100 families participated in workshops on hand washing
Activity 1.2.1 | Develop workshop lesson plan
2 | Background research on evidence-based best practices in hand-washing | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.2.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.2.3 | Present workshops
2 | Health and hygiene program team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
7 | Bars of soap, towels to give away | Unit | 100 | 2 | 200 |  | 200
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.2.4 | Provide 3 months follow-up
2 | Health and hygiene program team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 1.3 | 100 families participated in workshops on of point of use water purification
Activity 1.3.1 | Develop workshop lesson plan; collect/develop workshop materials
2 | Background research on evidence-based best practices in POU water purification | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.3.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.3.3 | Present workshops
2 | Health and hygiene program team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
7 | Point of use water filter for demonstration | Unit | 1 | 50 | 50 |  | 50
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.3.4 | Provide 3 months follow-up
2 | Health and hygiene program team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 1 | 360 |  | 360 | 360
10 | Office expenses | Unit | 1 | 250 | 250 |  | 250
Output 1.4 | 100 families participated in workshops on kitchen hygiene
Activity 1.4.1 | Develop workshop lesson plan
2 | Background research on evidence-based best practices in kitchen hygiene | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.4.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.4.3 | Present workshops
2 | Health and hygiene program team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
7 | Collect/develop workshop materials; kitchen hygiene | Unit | 100 | 2 | 200 |  | 200
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 1.4.4 | Provide 3 months follow-up
2 | Health and hygiene program team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Sub-Goal 2 | Family Garden and Nutrition Program
Output 2.1 | 100 families participated in workshops on family nutrition and home gardens
Activity 2.1.1 | Develop workshop lesson plan; collect/develop workshop materials
2 | Background research on evidence-based family gardens and nutrition | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.5 | 360 |  | 180 | 180
10 | Office expenses | Unit | 0.5 | 250 | 125 |  | 125
Activity 2.1.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 2.1.3 | Present workshops
2 | Family garden and nutrition program team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
2 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 | 62.5 | 125
Activity 2.1.4 | Provide 3 months follow-up
2 | Family garden and nutrition program team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 2.2 | Workshops on planning and planting home gardens for family nutrition have been presented to 100 families
Activity 2.2.1 | Develop workshop lesson plan; collect/develop workshop materials plan
2 | Background research on evidence-based best practices in gardening for nutrition | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 2.2.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 2.2.3 | Present workshops
2 | Family garden and nutrition program team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
7 | Purchase shovels, machetes, rakes, trowels, watering cans for workshop | Unit | 1 | 200 | 200 |  | 200
7 | Purchase seeds for workshops | Unit | 1 | 100 | 100 |  | 100
7 | Purchase seeds for 100 family gardens | Unit | 100 | 20 | 2000 |  | 2000
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 2.2.4 | Provide 6 months follow-up
2 | Family garden and nutrition program team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Sub-Goal 3 | Agricultural Income Generation Program |  |  | $US
Output 3.1 | 100 families in 4 villages participated in the organization of a community based Farmer's Association
Activity 3.1.1 | Develop workshop lesson plan
1 | Project director forms 2 person CSA and agricultural income generation team | Month | 0.5 | 800 |  | 400 | 400
2 | Background research on evidence-based best practices in agricultural income generation | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 3.1.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 3.1.3 | Present workshops
2 | CSA program team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 3.1.4 | Volunteers for an interim management committee
2 | CSA program team | Month | 0 | 1200 | 0 |  | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
Activity 3.1.5 | Formally establish the committee
2 | CSA program team | Month | 0 | 1200 | 0 |  | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
Activity 3.1.6 | Discuss how the next three program outputs will be conducted over a 12 month period
2 | CSA program team | Month | 0 | 1200 | 0 |  | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
Activity 3.1.7 | Set date and venue to hold the first committee meeting - distribute responsibilities for meeting
2 | CSA program team | Month | 0 | 1200 | 0 |  | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
Output 3.2 | A survey was conducted with 25 local/regional businesses and markets
Activity 3.2.1 | Develop a survey form for surveying local businesses
2 | Background research on evidence-based best practices in market surveys | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Faciliate workshop with committee members | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA program team finalize survey | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 3.2.2 | Develop a list of potential businesses that could be interviewed
2 | Interview community members for ideas for businesses to survey | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a business/market list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit |  | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 3.2.3 | Determine who will conduct the surveys
2 | CSA program team | Month | 0.5 | 1200 | 600 |  | 600
6 | Interview community members for ideas for who conducts the survey | Unit | 0 | 1200 | 0 |  | 0
6 | CSA program team finalizes list | Unit | 0 | 1200 | 0 |  | 0
5 | Travel expenses | Unit | 0 | 30 | 0 | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
Activity 3.2.4 | Conduct the surveys and compile the information
2 | CSA program team | Month | 1.5 | 1200 | 1800 |  | 1800
2 | Conduct the surveys | Month | 0 | 1200 | 0 |  | 0
2 | Compile the information | Month | 0 | 1200 | 0 |  | 0
5 | Travel expenses | Unit | 25 | 30 |  | 750 | 750
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 3.3 | Market links were established between 50 farmers in the Farmer's Association and five businesses
Activity 3.3.1 | Discuss with Farmer's Association which businesses are the best fit
2 | Share with Association members the results of the survey | Month | 0.25 | 1200 | 300 |  | 300
2 | Prioritize the most appropriate businesses for the Association | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.5 | 360 |  | 180 | 180
10 | Office expenses | Unit | 0.5 | 250 | 125 |  | 125
Activity 3.3.2 | Vote to prioritize the top businesses to approach about establishing a market link
2 | Use participatory methods to select the most appropriate businesses to approach | Month | 0 | 1200 | 0 |  | 0
2 | Fnalize a business list | Month | 0 | 1200 | 0 |  | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
Activity 3.3.3 | Approach the top businesses to establish the market link
2 | Arrange appointments with the businesses | Month | 0.25 | 1200 | 300 |  | 300
6 | Negotiate a sales and marketing relationship | Unit | 0.25 | 1 | 0.25 |  | 0.25
6 | Develop & preliminary contracts | Unit | 0.25 | 25 | 6.25 |  | 6.25
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 3.3.4 | Ask the businesses if they would be willing to make an investment in farmer inputs and training program
2 | CSA Program Team | Month | 0.25 | 1200 | 300 |  | 300
2 | Revise and sign contracts | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 3.4 | Vocational training workshops were launched for the 50 farm families
Activity 3.4.1 | Ask members of the Farmer's Association what types of training they feel they need
2 | CSA Program Team | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 3.4.2 | Ask the businesses what types of training they feel the farmers will need
2 | Interview businesses on training needs | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a training list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 3.4.3 | Develop a curriculum, workshop materials and schedule for leading individual training sessions
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
6 | Develop a draft curriculum to share with committee members | Unit | 0.25 | 1200 | 300 |  | 300
| Revise curriculum based upon committee input |  | 0.25 | 1200
2 | Write plan for workshops | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Sub-Goal 4 | Climate Change Awareness Program
Output 4.1 | 100 families participated in a workshop and survey to identify their knowledge of climate change
Activity 4.1.1 | Develop workshop lesson plan; collect/develop workshop materials
2 | Background research on evidence-based climate change training | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 4.1.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 4.1.3 | Present workshops
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
2 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 | 62.5 | 125
Activity 4.1.4 | Compile the information derived from the survey
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 4.2 | 100 families participated in a consciousness-raising workshops about climate change, its near and long-term impacts, and the need for a long-term adaptation plan
Activity 4.2.1 | Develop workshop lesson plan; collect/develop workshop materials plan
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 4.2.2 | Arrange workshop meetings with communities
2 | Interview commit he members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 4.2.3 | Present workshops
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 4.2.4 | Open discussion about the need for a long-term adaptation plan
2 | CSA Program Team | Month | 0 | 1200 | 0 |  | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
Sub-Goal 5 | Climate Smart Agricultural Practices Program |  |  | $US
Output 5.1 | An expert specialist/extension agent in soil, water and agriculture was identified
Activity 5.1.1 | Define the experts job description and terms of reference
2 | CSA Program Team | Month | 0.5 | 800 |  | 400 | 400
2 | Background research on expert requirements | Month | 0.25 | 1200 | 300 |  | 300
2 | Write job description and terms of reference | Month | 0.25 | 1200 | 300 |  | 300
2 | Present to committee members for input | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.1.2 | Advertise for the position and hold interviews
2 | Research appropriate locations to advertise the position | Month | 0.25 | 1200 | 300 |  | 300
2 | Receive applications and develop a list of finalists | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview applicants and prioritize the most appropriate applicants for the community | Month | 0.25 | 1200 | 300 |  | 300
2 | Share the prioritized list with committee members and select most appropriate applicant | Month | 0.25 | 1200 | 300 |  | 300
2 | Introduce finalist to committee members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.1.3 | Contract with finalist
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Write a contract | Unit | 0.25 | 1200 | 300 |  | 300
6 | Sign contract with finals | Unit | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.1.4 | Develop a master plan of the workshops
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
2 | Work with CSA expert to develop an activity list for workshops | Month | 1 | 1200 | 1200 |  | 1200
2 | Work with CSA expert to develop a master plan and curriculum for the workshops | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 2 | 30 |  | 60 | 60
3 | Assistant | Month | 1 | 360 |  | 360 | 360
10 | Office expenses | Unit | 1 | 250 | 250 |  | 250
Output 5.2 | 100 families participated in surveys and interviews to collect traditional knowledge on agriculture
Activity 5.2.1 | Develop workshop lesson plan; collect/develop workshop materials plan
2 | Background research on evidence-based best practices in collecting traditional knowledge | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.2.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.2.3 | Present workshops
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.2.4 | Compile the information derived from the survey
2 | Health and hygiene program team | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 5.3 | Workshops on participatory mapping of local crop challenges related to climate change
Activity 5.3.1 | Develop workshop lesson plan; collect/develop workshop materials
2 | Background research on evidence-based best practices in participatory mapping | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.3.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.3.3 | Present workshops
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.3.4 | Provide 3 months follow-up
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 1 | 360 |  | 360 | 360
10 | Office expenses | Unit | 1 | 250 | 250 |  | 250
Output 5.4 | Extension agent visited affected farmers to identify exact CC impacts to crop production
Activity 5.4.1 | Agricultural extension officers plan format and timing for farm visits
2 | Background research on evidence-based best practices in hand-washing | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.4.2 | Work with community to identify farms that will be visited by agriculture extension officers and set date for visits
2 | Interview community members and extension agentfor the most representative farms to visit | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.4.3 | Four days of farm visits and discussions with farmers
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Assemble survey materials | Unit | 0.25 | 1200 | 300 |  | 300
6 | Collect farm data | Unit | 0.25 | 25 | 6.25 |  | 6.25
5 | Travel expenses | Unit | 8 | 30 |  | 240 | 240
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.4.4 | Agricultural extension officers compile results of farm visits
2 | CSA Program Team | Month | 0.25 | 1200 | 300 |  | 300
2 | Compile the results of farm visit | Unit | 0.25 | 1200 |  | 300 | 300
2 | Present results to committee | Unit | 0.25 | 1200 |  | 300 | 300
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 5.5 | Farmer's Association committee developed a plan for an improvement in productivity
Activity 5.5.1 | Develop workshop plan
2 | Background research on evidence-based best practices in CSA Agriculture | Month | 0.25 | 1200 | 300 |  | 300
2 | Write plan for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Share the plan with committee members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.5.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.5.3 | Present plan for workshops to association members
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | Extension agent to meet with Association committee to finalize the plan | Unit | 0.1 | 1200 | 120 |  | 120
2 | Finalized plan is written and printed out for presentation to association members | Unit | 0.1 | 1200 | 120 |  | 120
2 | Plan is presented to association members | Unit | 0.1 | 1200 | 120 |  | 120
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 5.6 | One pilot plot in each village was established demonstrating better cultivation practices
Activity 5.6.1 | Develop workshop lesson plan; collect/develop workshop materials plan
2 | Background research on evidence-based best practices on developing pilot plots | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best locations for pilot plots | Month | 0.25 | 1200 | 300 |  | 300
2 | Consult with committee about the locations and about their greed contributions to the pilot plots | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.6.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.6.3 | Present workshops
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Write lesson plan and how-to cards for workshops | Unit | 0.25 | 1200 | 300 |  | 300
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
7 | Purchase shovels, machetes, rakes, hoes for workshop | Unit | 10 | 40 | 400 |  | 400
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.6.4 | Provide 3 months follow-up
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 5.7 | Workshops on soil restoration and conservation techniques
Activity 5.7.1 | Develop workshop lesson plan; collect/develop workshop materials
2 | Background research on evidence-based best practices in soil restoration | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.7.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.7.3 | Present workshops
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
7 | Bring shovels, machetes, rakes, hoes for workshop | Unit | 0 | 40 | 0 |  | 0
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.7.4 | Provide 3 months follow-up
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 5.8 | Workshops on water conservation and management techniques
Activity 5.8.1 | Develop workshop lesson plan; collect/develop workshop materials plan
2 | Background research on evidence-based best practices in water conservation and management | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.8.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.8.3 | Present workshops
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
7 | Bring shovels, machetes, rakes, hoes for workshop | Unit | 0 | 40 | 0 |  | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.8.4 | Provide 3 months follow-up
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Output 5.9 | Workshops on early maturing and/or drought resistant crops/varieties
Activity 5.9.1 | Develop workshop lesson plan; collect/develop workshop materials plan
2 | Background research on evidence-based best practices in resilient crops | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.9.2 | Arrange workshop meetings with communities
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.9.3 | Present workshops
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
7 | Collect/develop workshop materials; seed and crop examples | Unit | 100 | 4 | 400 |  | 400
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Activity 5.9.4 | Provide 3 months follow-up
2 | CSA Program Team | Month | 1 | 1200 |  | 1200 | 1200
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Total |  |  |  |  | 77447.75 | 20465 | 97912.75
Percentage |  |  |  |  | 79.1% | 20.9%
Categories
1 | Director
2 | Field Staff
3 | Assistant
4 | Utilities
5 | Travel
6 | Classroom materials, publishing, printing and photocopying
7 | Product Purchases
8 | Scholarships
9 | Rent
10 | Office

## Budget by Category
1 | Project director forms 2 person health, hygiene, nutrition and garden program team | Month | 0.5 | 800 |  | 400 | 400
1 | Project director forms 2 person CSA and agricultural income generation team | Month | 0.5 | 800 |  | 400 | 400
2 | Background research on evidence-based best practices in hand-washing | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | Health and hygiene program team | Month | 0.5 | 1200 | 600 |  | 600
2 | Health and hygiene program team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in hand-washing | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | Health and hygiene program team | Month | 0.5 | 1200 | 600 |  | 600
2 | Health and hygiene program team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in POU water purification | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | Health and hygiene program team | Month | 0.5 | 1200 | 600 |  | 600
2 | Health and hygiene program team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in kitchen hygiene | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | Health and hygiene program team | Month | 0.5 | 1200 | 600 |  | 600
2 | Health and hygiene program team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based family gardens and nutrition | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | Family garden and nutrition program team | Month | 0.5 | 1200 | 600 |  | 600
2 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
2 | Family garden and nutrition program team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in gardening for nutrition | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | Family garden and nutrition program team | Month | 0.5 | 1200 | 600 |  | 600
2 | Family garden and nutrition program team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in agricultural income generation | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA program team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA program team | Month | 0 | 1200 | 0 |  | 0
2 | CSA program team | Month | 0 | 1200 | 0 |  | 0
2 | CSA program team | Month | 0 | 1200 | 0 |  | 0
2 | CSA program team | Month | 0 | 1200 | 0 |  | 0
2 | Background research on evidence-based best practices in market surveys | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Faciliate workshop with committee members | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA program team finalize survey | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for ideas for businesses to survey | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a business/market list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA program team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA program team | Month | 1.5 | 1200 | 1800 |  | 1800
2 | Conduct the surveys | Month | 0 | 1200 | 0 |  | 0
2 | Compile the information | Month | 0 | 1200 | 0 |  | 0
2 | Share with Association members the results of the survey | Month | 0.25 | 1200 | 300 |  | 300
2 | Prioritize the most appropriate businesses for the Association | Month | 0.25 | 1200 | 300 |  | 300
2 | Use participatory methods to select the most appropriate businesses to approach | Month | 0 | 1200 | 0 |  | 0
2 | Fnalize a business list | Month | 0 | 1200 | 0 |  | 0
2 | Arrange appointments with the businesses | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.25 | 1200 | 300 |  | 300
2 | Revise and sign contracts | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview businesses on training needs | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a training list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
2 | Write plan for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Background research on evidence-based climate change training | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview commit he members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA Program Team | Month | 0 | 1200 | 0 |  | 0
2 | CSA Program Team | Month | 0.5 | 800 |  | 400 | 400
2 | Background research on expert requirements | Month | 0.25 | 1200 | 300 |  | 300
2 | Write job description and terms of reference | Month | 0.25 | 1200 | 300 |  | 300
2 | Present to committee members for input | Month | 0.25 | 1200 | 300 |  | 300
2 | Research appropriate locations to advertise the position | Month | 0.25 | 1200 | 300 |  | 300
2 | Receive applications and develop a list of finalists | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview applicants and prioritize the most appropriate applicants for the community | Month | 0.25 | 1200 | 300 |  | 300
2 | Share the prioritized list with committee members and select most appropriate applicant | Month | 0.25 | 1200 | 300 |  | 300
2 | Introduce finalist to committee members | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
2 | Work with CSA expert to develop an activity list for workshops | Month | 1 | 1200 | 1200 |  | 1200
2 | Work with CSA expert to develop a master plan and curriculum for the workshops | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in collecting traditional knowledge | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | Health and hygiene program team | Month | 0.25 | 1200 | 300 |  | 300
2 | Background research on evidence-based best practices in participatory mapping | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in hand-washing | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members and extension agentfor the most representative farms to visit | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA Program Team | Month | 0.25 | 1200 | 300 |  | 300
2 | Compile the results of farm visit | Unit | 0.25 | 1200 |  | 300 | 300
2 | Present results to committee | Unit | 0.25 | 1200 |  | 300 | 300
2 | Background research on evidence-based best practices in CSA Agriculture | Month | 0.25 | 1200 | 300 |  | 300
2 | Write plan for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Share the plan with committee members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | Extension agent to meet with Association committee to finalize the plan | Unit | 0.1 | 1200 | 120 |  | 120
2 | Finalized plan is written and printed out for presentation to association members | Unit | 0.1 | 1200 | 120 |  | 120
2 | Plan is presented to association members | Unit | 0.1 | 1200 | 120 |  | 120
2 | Background research on evidence-based best practices on developing pilot plots | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best locations for pilot plots | Month | 0.25 | 1200 | 300 |  | 300
2 | Consult with committee about the locations and about their greed contributions to the pilot plots | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in soil restoration | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in water conservation and management | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
2 | Background research on evidence-based best practices in resilient crops | Month | 0.25 | 1200 | 300 |  | 300
2 | Write lesson plan and how-to cards for workshops | Month | 0.25 | 1200 | 300 |  | 300
2 | Rehearse workshop with team members | Month | 0.25 | 1200 | 300 |  | 300
2 | Interview community members for the best time, location for the workshop | Month | 0.25 | 1200 | 300 |  | 300
2 | Develop a participant list | Month | 0.25 | 1200 | 300 |  | 300
2 | CSA Program Team | Month | 0.5 | 1200 | 600 |  | 600
2 | CSA Program Team | Month | 1 | 1200 | 1200 |  | 1200
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 1 | 360 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 1 | 360 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.5 | 360 |  | 180 | 180
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0 | 360 |  | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
3 | Assistant | Month | 0 | 360 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0 | 360 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.5 | 360 |  | 180 | 180
3 | Assistant | Month | 0 | 360 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0 | 360 |  | 0 | 0
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 1 | 360 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 1 | 360 |  | 360 | 360
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
3 | Assistant | Month | 0.25 | 360 |  | 90 | 90
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit |  | 30 |  | 0 | 0
5 | Travel expenses | Unit | 0 | 30 | 0 | 0 | 0
5 | Travel expenses | Unit | 25 | 30 |  | 750 | 750
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 2 | 30 |  | 60 | 60
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 8 | 30 |  | 240 | 240
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 5 | 30 |  | 150 | 150
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 1 | 30 |  | 30 | 30
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
5 | Travel expenses | Unit | 0 | 30 |  | 0 | 0
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 3 | 30 |  | 90 | 90
5 | Travel expenses | Unit | 12 | 30 |  | 360 | 360
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Interview community members for ideas for who conducts the survey | Unit | 0 | 1200 | 0 |  | 0
6 | CSA program team finalizes list | Unit | 0 | 1200 | 0 |  | 0
6 | Negotiate a sales and marketing relationship | Unit | 0.25 | 1 | 0.25 |  | 0.25
6 | Develop & preliminary contracts | Unit | 0.25 | 25 | 6.25 |  | 6.25
6 | Develop a draft curriculum to share with committee members | Unit | 0.25 | 1200 | 300 |  | 300
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Write a contract | Unit | 0.25 | 1200 | 300 |  | 300
6 | Sign contract with finals | Unit | 0.25 | 1200 | 300 |  | 300
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Assemble survey materials | Unit | 0.25 | 1200 | 300 |  | 300
6 | Collect farm data | Unit | 0.25 | 25 | 6.25 |  | 6.25
6 | Write lesson plan and how-to cards for workshops | Unit | 0.25 | 1200 | 300 |  | 300
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
6 | Print out hand-outs and how-to cards | Unit | 100 | 1 | 100 |  | 100
6 | Collect/develop workshop materials; paper, pens | Unit | 1 | 25 | 25 |  | 25
7 | Bars of soap, towels to give away | Unit | 100 | 2 | 200 |  | 200
7 | Point of use water filter for demonstration | Unit | 1 | 50 | 50 |  | 50
7 | Collect/develop workshop materials; kitchen hygiene | Unit | 100 | 2 | 200 |  | 200
7 | Purchase shovels, machetes, rakes, trowels, watering cans for workshop | Unit | 1 | 200 | 200 |  | 200
7 | Purchase seeds for workshops | Unit | 1 | 100 | 100 |  | 100
7 | Purchase seeds for 100 family gardens | Unit | 100 | 20 | 2000 |  | 2000
7 | Purchase shovels, machetes, rakes, hoes for workshop | Unit | 10 | 40 | 400 |  | 400
7 | Bring shovels, machetes, rakes, hoes for workshop | Unit | 0 | 40 | 0 |  | 0
7 | Bring shovels, machetes, rakes, hoes for workshop | Unit | 0 | 40 | 0 |  | 0
7 | Collect/develop workshop materials; seed and crop examples | Unit | 100 | 4 | 400 |  | 400
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 1 | 250 | 250 |  | 250
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 1 | 250 | 250 |  | 250
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.5 | 250 | 125 |  | 125
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 | 62.5 | 125
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.5 | 250 | 125 |  | 125
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 | 62.5 | 125
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0 | 250 | 0 |  | 0
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 1 | 250 | 250 |  | 250
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 1 | 250 | 250 |  | 250
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
10 | Office expenses | Unit | 0.25 | 250 | 62.5 |  | 62.5
Categories
1 | Director
2 | Field Staff
3 | Assistant
4 | Utilities
5 | Travel
6 | Classroom materials, publishing, printing and photocopying
7 | Product Purchases
8 | Scholarships
9 | Rent
10 | Office